## Sheet1
S.No | Feedback / Issue | Reported Date | Responsibillty | Status | Closed Date | Estimated Hours
1 | Control Settings - when changing input type from text to numeric (or vice-versa) width and general validations should not be changed | 2019-04-04 | Front-End
2 | Control Settings - when selected input type is numeric with decimal then min & max should have decimals (ex: 1.00 & 5.00) | 2019-04-04 | Front-End
3 | Control Settings - Phone Number minlength and maxlength should not consider '-' for calculating length (that validation should be calcluated from front-end) | 2019-04-04 | Front-End
4 | Control Settings - when selected input type is date and has dependancy validation , the default value will be populated when the type is equal to ('=','>=','<=') | 2019-04-04 | Front-End |  |  | Done
5 | NewHire - while adding newhire , attachments are not getting uploaded | 2019-04-04 | Front-End |  |  | Done
6 | NewHire - Add newhire mail, excel doesnot have the Double Time Rate & Double Time Bill Rates are missing (when the value is empty) | 2019-04-04 | API |  |  | Done
7 | Newhire - Add / Edit NewHire Double Time Rates textboxes are getting closer to above Pay Rates | 2019-04-04 | Front-End |  |  | Done
8 | Control Settings - when selected input type is date in dependancy validation other fields dropdown should display label name | 2019-04-04 | Front-End |  |  | Done
9 | Control Settings - Radio Button is dropped default values of custom list should have deleted buttons (Validation of having minimum 2 options for radio button should be validated at the save level) | 2019-04-04 | Front-End | Done |  | 1
10 | Workflow - Add workflow , static step should have Payroll , EEO , Contractor Info checkboxes row-wise) | 2019-04-04 | Front-End |  |  | Done
11 | Deployment - Validation Messages should be configured and no deployment should be done if any changes in messages | 2019-04-04 | Front-End/API
12 | Dynamic Json - if the selected input type is numeric with decimal the value should have .00 to be added dynamically | 2019-04-04 | Front-End
13 | Initiate Onboarding -Inititated Mail received to yahoo gets a spam file at the end. | 2019-04-04 | API |  |  | Done
14 | NewHire Webforms - Label name edit should have an API call to maintain unique and check the associations w.r.t Email Templates | 2019-04-04 | Front-End/API |  |  | 3 + 8
15 | Design Webforms - Drop Controls should happen anywhere in drop zone(even between controls) | 2019-04-02 | Front-End
16 | Control Settings - Show and Hide Controls based on Radio & Dropdown option | 2019-04-02 | Front-End |  |  | Done
17 | Control Settings - Google Map settings , selected address populating City , State, ZipCode w.r.t selected controls | 2019-04-02 | Front-End |  |  | Done
18 | Control Settings - Confirm Account Number & Confirm Routing Number Validations | 2019-04-02 | Front-End |  |  | Done
19 | Design Webforms - Saving a sub webform, decreasing the number of instances needs an API call | 2019-04-02 | Front-End/API |  |  | Done
20 | While dragging the control from toolbox and dropping over the non-layout part of the webform, update the existing icon colour from black to ‘Red’. | 2019-03-27 | Front-End | Differed
21 | Control Settings - When Field Type is changed scroll goes to bottom automatically in popup | 2019-03-04 | Front-End |  |  | R&D
22 | Control Settings - Field Type: Make it to alphabetical order. | 2019-03-04 | Front-End | Done |  | 1
23 | Control Settings - Add Hide and Unhide functionality for currentDate. | 2019-03-04 | Front-End | Done |  | 1
24 | Control Settings - Date validations when having a dependency on other date control. | 2019-03-04 | Front-End |  |  | Done
25 | Add Tooltip (help text) when drag and dropping radio or checkbox controls in Common Details Web Form like ‘ For controls like Radio and Checkbox value should be same in Webform and PDF’ | 2019-03-04 | Front-End | Done |  | 2
26 | Make the checkbox size bigger and align to center in Edit Document Webform. | 2019-03-04 | Front-End | Done |  | 1
27 | Add new filter for Email in New Hire list. | 2019-03-04 | Front-End |  |  | 1
28 | Re-Hire : Revise the fields that should be auto-populated. | 2019-03-04 | Front-End/API | Done |  | 4
29 | Preview Validate: After clicking on Submit button, make the scroll to required field. | 2019-03-04 | Front-End
30 | Mouse pointer on scrollbar for Workflow Folders Drag Section should be changed (presently displayed as Move) | 2019-03-04 | Front-End | Done |  | 2
31 | Remove (Current Date + 7 days) in date settings | 2019-04-08 | Front-End |  |  | Done
32 | Add 15 years & 18 years options in date control for date validation | 2019-04-08 | Front-End | Done |  | 3
33 | Expand and Collapse Custom Webforms with checkboxes in Add Workflow static step with 10 records at a time and more button provision | 2019-04-16 | Front-End
34 | Navigation restrictions in Candidate Module based on saved webforms | 2019-04-08 | Front-End |  |  | Done
35 | Spinners for webform pages and documents both HR and Coandidate Side | 2019-04-16 | Front-End | Done |  | 1
36 | Check the documents order of display in both Candidate and HR dashboards | 2019-04-24 | Front-End | Done |  | 1
37 | Show Controls also have dividers for show and hide | 2019-04-24 | Front-End |  |  | 2
38 | Common Details Next icon should bottom right | 2019-04-24 | Front-End | Done |  | 1
39 | Time delay in the controls | 2019-04-24 | Front-End |  |  | R&D
40 | Calendar control should consider m/d/yyyy besides mm/dd/yyyy | 2019-04-24 | Front-End
41 | Saved attachment in NewHire should be deleted after the confirmation popup | 2019-04-24 | Front-End | Done |  | 1
42 | View Saved attachment is not able view(View Button is not working) | 2019-04-24 | Front-End | Done |  | 1
43 | NewHires list options should be View instead of View Newhire | 2019-04-24 | Front-End |  |  | Done
44 | Input fields of numeric type should be having the placeholder with max and min values | 2019-04-24 | Front-End |  |  | 2
45 | showControls : [] is missing when HR uploads a document with radio buttons | 2019-04-24 | Front-End |  |  | Done
46 | mask data & google maps checkboxes should get checked vice-versa | 2019-04-24 | Front-End | Done |  | 1
47 | Restricting radio button values should not be above 127 characters(Design Webforms & Documents) | 2019-04-08 | Front-End |  |  | 3
48 | Common Details first time save not redirected to BGV or the next (due to disabled nav tabs) | 2019-04-24 | Front-End |  |  | Done
49 | Control Settings : Re-arrange such that layout & width options should one group , validation other group | 2019-04-24 | Front-End
50 | Master Controls like Hire Category should not be able to delete or edit the option values | 2019-04-08 | Front-End | Done |  | 2
51 | HR Dashboard - New Hires Changes section changes | 2019-04-08 | Front-End |  |  | 16
52 | Display ‘Custom web forms’ under separate tab like folders. HR user should be able to drag & drop the Custom webfoms ONLY against the first Static step.In case HR user is trying to drag and drop the Custom Webforms against other steps display the Toaster message ‘Custom webforms should be mapped ONLY against the first static step <Step Name> | 2019-04-26 | Front-End
53 | When HR user sets Selected Date control value equals to current date, that Date control should be shown in disabled mode to the Candidate. | 2019-04-26 | Front-End | Done |  | 2
54 | For Hand Sign documents – Display the upload & download buttons in a modal window like any other read only PDF documents. | 2019-04-26 | Front-End | Done |  | 1
55 | Remove Skip link while displaying the PDF document (after filling the associated dynamic webform) to sign. | 2019-04-26 | Front-End |  |  | Done
56 | After Candidate completing ALL the pending documents currently success popup window is displayed. In this pop up window remove the ‘note’ section. | 2019-04-26 | Front-End | Done |  | 1
57 | Candidate should still be able to log into the Onboarding portal, even after HR approves ALL the pending documents. Candidate Onboarding portal access related content should be updated in the Notification which goes to the candidate in this scenario. | 2019-04-26 | API | Done |  | 4
58 | Signup screen - Add google maps for country | 2019-04-26 | Front-End/API | Done |  | 1+1
59 | Clients List API should be added to multiple controls in Webform | 2019-04-26 | Front-End |  |  | 1
60 | Add Workflow : Drag and Drop dynamic webform ,webform icon missing in the drop container | 2019-04-26 | Front-End |  |  | 1
61 | General Settings : Add New two input fields , functionality for saving BGV additional records | 2019-04-26 | API |  |  | 2 + 2